## Costs_Period M1-M12
Country | Partner | Personnel Costs |  |  |  |  | Travel Costs |  |  |  |  | Costs for Durable Equipment |  |  |  |  | Costs for Consumables |  |  |  |  | Costs for Subcontracting |  |  |  |  | Other Costs |  |  |  |  | Sum Direct Costs |  |  |  | Indirect Costs |  |  |  |  | Overall costs to the JU (direct & indirect costs)
|  | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total (Other costs) | Fundamental Costs | Industrial Costs | Experimental Costs | Total (Direct Costs) | Fundamental Costs | Industrial Costs | Experimental Costs | Explanation | Total (Indirect Costs) |  | comments: missing information will be provided as soon as possible
AT | 01_AVL |  | 1148964.0415 |  |  | 1148964.0415 |  | 40135.61 |  | travel expenses for CRYSTAL F2F meetings (kick-off meeting, Working and Consolidation Event, Technical Board Meetings), ARTEMIS-IA Co-Summit, ARTEMIS Brokerage Event, ProStep Event, CRYSTAL F2F meetings, CRYSTAL workshops with other partners | 40135.61 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 3860.95 |  | CRYSTAL Homepage, dissemination material | 3860.95 | 0 | 1192960.6015 | 0 | 1192960.6015 |  | 936405.6938 |  | The used rate is 81,5 % of the personnel costs, as allowed by National Funding Authority | 936405.6938 | 2129366.2954
FR | 02_A-F | 130000 |  |  | 9 PM | 130000 | 2000 |  |  |  | 2000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 132000 | 0 | 0 | 132000 |  |  |  |  | 0 | 132000 | indirect costs missing
DE | 03_A-G | 121000 |  |  | app. 10 PM | 121000 | 3000 |  |  |  | 3000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 124000 | 0 | 0 | 124000 | 5000 |  |  |  | 5000 | 129000
UK | 04_A-UK | 180000 |  |  | 15 PM | 180000 | 2000 |  |  |  | 2000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 182000 | 0 | 0 | 182000 |  |  |  |  | 0 | 182000 | indirect costs missing
IT | 05_ALA |  | 255000 |  | Corresponding to senior engineers working, at least partially, on SP1, SP2 and SP6. WP202 and WP602 have been led by ALA. | 255000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 255000 | 0 | 255000 |  | 127500 |  | The used rate is flat, corresponding to 50% of the personnel costs, as allowed by National Funding Authority | 127500 | 382500
FR | 06_ALS |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | no input yet
IT | 07_ASTS |  | 45518.9852 | 4918.6977 | 10,25 PMs | 50437.6829 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 45518.9852 | 4918.6977 | 50437.6829 |  | 22759.4926 | 2459.3488 | Indirect personnel costs | 25218.8414 | 75656.5243
SE | 08_ARCC | 70036 |  |  |  | 70036 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 70036 | 0 | 0 | 70036 | 14007 |  |  |  | 14007 | 84043
SE | 09_ARCT |  | 91200 |  |  | 91200 |  | 1900 |  |  | 1900 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 93100 | 0 | 93100 |  | 4164 |  |  | 4164 | 97264
AT | 10_AIT |  | 247165.5864 |  |  | 247165.5864 |  | 5923.47 |  |  | 5923.47 |  |  |  |  | 0 |  | 13603.32 |  |  | 13603.32 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 266692.3764 | 0 | 266692.3764 |  | 172991.1939 |  |  | 172991.1939 | 439683.5703
DE | 11_AVL-S |  | 143806.7 |  | 13,55 MM Lead Engineer / 6,05 MM Engineer | 143806.7 |  | 7223.63 |  | F2F meetings: Kick-off meeting, Working and Consolidation Event, SP Workshops, Synchronisation meetings, … | 7223.63 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 151030.33 | 0 | 151030.33 |  | 86053.44 |  | Indirect personnel costs | 86053.44 | 237083.77
DE | 12_AVL-R |  | 166117 |  | 10,6MM Principal / 11,4MM Dipl.-Ing. | 166117 |  | 5064 |  | F2F meetings: Kick-off Meeting, Working and Consolidation Event, SP/WP Workshops, Synchronisation meetings, … | 5064 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 171181 | 0 | 171181 |  |  |  |  | 0 | 171181 | indirect costs missing
BE | 13_BARCO |  |  | 1025212 | Personnel cost | 1025212 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 307564 | 30% of personnel costs, rule set by national funding institution | 307564 | 0 | 0 | 1332776 | 1332776 |  |  | 205042 | 20% of personnel costs, rule set by national funding institution | 205042 | 1537818
ES | 14_REUSE | 77191.54 |  |  |  | 77191.54 |  |  |  |  | 0 | 3799 |  |  |  | 3799 |  |  |  |  | 0 |  |  |  |  | 0 | 2667 |  |  |  | 2667 | 83657.54 | 0 | 0 | 83657.54 | 15438.31 |  |  |  | 15438.31 | 99095.85
IT | 15_CRF |  | 61609.84 |  | Resources employed | 61609.84 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 10000 |  | Support to use case modeling implementation | 10000 |  |  |  |  | 0 | 0 | 71609.84 | 0 | 71609.84 |  | 30804.92 |  | Resources employed | 30804.92 | 102414.76
SE | 16_CTH |  | 63595 |  | Personal costs to cover work done in Crystal | 63595 |  | 10406 |  | Travel costs for conference attendance and guests | 10406 |  |  |  |  | 0 |  | 2836 |  | PC for doing Crystal work related to modeling and verification | 2836 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 76837 | 0 | 76837 |  | 29186 |  | indirect costs | 29186 | 106023
UK | 17_CIC |  | 46968 |  | Labour cost for the year | 46968 |  | 2444 |  | Travel to the general meeting in May 2013 and the second IAS conference and the Workshop meeting EADS Aribus in Bremen | 2444 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 49412 | 0 | 49412 |  | 2540 |  | Overhead costs such as Utility costs etc. | 2540 | 51952
DE | 18_DAIMLER | 280000 |  |  |  | 280000 | 3000 |  |  |  | 3000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 283000 | 0 | 0 | 283000 | 11000 |  |  |  | 11000 | 294000
DE | 19_EADS-CAS |  | 286562.71 |  |  | 286562.71 |  | 4491.87 |  |  | 4491.87 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 291054.58 | 0 | 291054.58 |  | 45936 |  |  | 45936 | 336990.58
DE | 20_EADS IW-G |  | 295354.45 |  |  | 295354.45 |  | 10688.35 |  |  | 10688.35 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 5933.44 |  |  | 5933.44 | 0 | 311976.24 | 0 | 311976.24 |  | 152222.75 |  |  | 152222.75 | 464198.99
FR | 21_EADS IW-F |  | 24543 |  |  | 24543 |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 24543 | 0 | 24543 |  | 31170 |  |  | 31170 | 55713
UK | 22_EADS IW-UK |  | 58034 |  |  | 58034 |  | 5246 |  |  | 5246 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0 | 63280 | 0 | 63280 |  | 52812 |  |  | 52812 | 116092
FR | 23_Elektrobit | 104664 |  |  |  | 58034 |  |  |  |  | 0 | 3884.72 |  |  |  | 3884.72 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 108548.72 | 0 | 0 | 108548.72 | 1628.3 |  |  | management | 1628.3 | 110177.02
AT | 24_TUG | 0 | 27144.58 | 0 |  | 27144.58 | 0 | 17.2 | 0 | 0 | 17.2 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27161.78 | 0 | 27161.78 |  | 5428.916 |  |  | 5428.916 | 32590.696
IT | 25_FBK |  | 77847.74 |  |  | 77847.74 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 77847.74 | 0 | 77847.74 |  | 38923.87 |  |  | 38923.87 | 116771.61
DE | 26_FhG | 250237 |  |  |  | 250237 | 9435 |  |  |  | 9435 |  |  |  |  | 0 | 550 |  |  |  | 550 |  |  |  |  | 0 | 8934 |  |  |  | 8934 | 269156 | 0 | 0 | 269156 | 174833 |  |  |  | 174833 | 443989 | FHG and IESE
ES | 27_Tecnalia | 208719.88 |  |  |  | 208719.88 |  |  |  |  | 0 |  |  |  |  | 0 | 295 |  |  |  | 295 |  |  |  |  | 0 | 7364.33 |  |  |  | 7364.33 | 216379.21 | 0 | 0 | 216379.21 | 41743.98 |  |  |  | 41743.98 | 258123.19
ES | 28_GMV | 19967.25 |  |  |  | 19967.25 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 275 |  |  |  | 275 | 20242.25 | 0 | 0 | 20242.25 | 3993.45 |  |  |  | 3993.45 | 24235.7
CZ | 29_HON |  | 108255.0773 |  |  | 108255.0773 |  | 4469.4569 |  |  | 4469.4569 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1790.0392 |  |  | 1790.0392 | 0 | 114514.5734 | 0 | 114514.5734 |  | 22902.9147 |  |  | 22902.9147 | 137417.4881
UK | 30_IBM UK |  | 70153.54 |  |  | 70153.54 |  | 8018.72 |  |  | 8018.72 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 78172.26 | 0 | 78172.26 |  | 33533.59 |  |  | 33533.59 | 111705.85
UK | 31_IFX-UK | 283400 |  |  | 21.8 MM @ 13,000/MM | 283400 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 283400 | 0 | 0 | 283400 |  |  |  |  | 0 | 283400 | indirect costs missing
ES | 32_ITI | 242988.98 |  |  |  | 242988.98 |  |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 22950 |  |  |  | 22950 | 12151.99 |  |  |  | 12151.99 | 278090.97 | 0 | 0 | 278090.97 | 48597.7965 |  |  |  | 48597.7965 | 326688.7665
DE | 33_ITKE | 72578.12 |  |  |  | 72578.12 | 835.04 |  |  |  | 835.04 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 73413.16 | 0 | 0 | 73413.16 | 148988.42 |  |  |  | 148988.42 | 222401.58
AT | 34_VIF |  | 175518.97 |  | salaries of 1 Area Manager, 1 Lead Engineer, 1 Junior Researcher, 6 Senior Researcher, 1 Key Researcher , 1 Student Assistent | 175518.97 |  | 6954.6 |  | Projects meeting: in Vienna in May 2013, in Munich in November 2013, in Munich in Februar 2014, in Brüssel in Februar 2014, in Graz in March 2014. International conference on software reuse in Pisa in June 2013, Interoperatbility Converence in Eskiltuna (Sweden) in December 2013, International scientif change in Gent in June 2013, Berliner Requirements Engineering Symposium in Berlin in November 2013 | 6954.6 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 164.98 |  | literature | 164.98 | 0 | 182638.55 | 0 | 182638.55 |  | 52937 |  | overhead rate 30,16 % of personnel costs | 52937 | 235575.55
SE | 35_ALL4TEC |  | 165548 |  |  | 165548 |  | 2266 |  |  | 2266 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 167814 | 0 | 167814 |  | 112731 |  |  | 112731 | 280545
CZ | 36_MU | 24855 |  |  |  | 24855 | 6708 |  |  |  | 6708 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 31563 | 0 | 0 | 31563 | 6056 |  |  |  | 6056 | 37619
IT | 37_MATE | 147200 |  |  | 46 PM | 147200 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 147200 | 0 | 0 | 147200 | 22080 |  |  |  | 22080 | 169280
NL | 38_IBM NL |  | 97301.03 |  |  | 97301.03 |  | 4812.01 |  | Crystal kick-off meeting Vienna: 866,13 SDMD Conference Munich: 1163,96 Working & Consolidation Event Munich: 576,14 + 808,52 Working Session with Barco Belgium: 87,40 M9 review meeting Brussels: 457,60 Technical Board meeting Munich: 852,26 | 4812.01 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 102113.04 | 0 | 102113.04 |  | 48650.515 |  | 50% of the direct costs | 48650.515 | 150763.555
NL | 39_TNO |  | 363124.92 |  |  | 363124.92 |  | 8798.78 |  |  | 8798.78 |  | 0 |  |  | 0 |  | 1090.62 |  |  | 1090.62 |  | 60587.5 |  |  | 60587.5 |  | 183.67 |  |  | 183.67 | 0 | 433785.49 | 0 | 433785.49 |  | 575651.48 |  |  | 575651.48 | 1009436.97
FR | 40_Obeo |  |  | 229341 |  | 229341 |  |  | 7282 |  | 7282 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 236623 | 236623 |  |  | 154168 |  | 154168 | 390791
DE | 41_OFFIS | 201188.48 |  |  | 41.05 person months; work performed according to the plans in the technical annex and described in details in the progress report | 201188.48 | 17404.56 |  |  | Kick-off Meeting Wien (May 2013); WP6.7 kick-off Meeting Paris (June 2013); WP6.1 kick-off Munich (June 2013); IOS Workshop Munich (June 2013); Technical Management Meeting Graz (Aug 2013); WP6.7 Meeting Madrid (Aug 2013); Meeting with KTH Hamburg (Sep 2013); SP2 Meeting Toulouse (Sep 2013); CRYSTAL Plenary Meeting Munich (Nov 2013); WP6.7 and WP2.4 Synchronization Meeting Paris (Jan 2014); Standardization Workin Group Meeting Brussels (Jan 2014); WP3.4 Meeting Graz (March 2014); ARTEMIS Meeting (Mar 2014); IOS Meeting with Airbus Hamburg (Mar 2014); Technical Board Workshop Munich (Apr 2014); | 17404.56 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 218593.04 | 0 | 0 | 218593.04 | 30068.93 |  |  | flat rate based on personnel costs | 30068.93 | 248661.97 | Total costs on national level are 250.142,94 including 1480,97 for VAT which are eligable on national level but not on European level
ES | 42_ORB | 61203 |  |  | Jorge Robles, Luis Ramírez and Javier Donaire effort in WP2.5, WP6.10 and WP6.11 | 61203 |  |  |  |  | 0 | 723.5 |  |  | 3x HP notebooks | 723.5 | 1316 |  |  | 1x IBM Rationale Rhapsody Licence | 1316 |  |  |  |  | 0 | [5 empty] | 63242.5 | 0 | 0 | 63242.5 | 12240 |  |  | 20% of Personnel | 12240 | 75482.5
DE | 43_PTC | 25500 |  |  | 3 Persons Month | 25500 |  | 5300 |  | to Workshops, Synchronisation meetings, … | 5300 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 25500 | 5300 | 0 | 30800 | 5100 |  |  |  | 5100 | 35900
NL | 44_PS-Tech | 115078 |  |  | 13.5 MM | 115078 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 3169 |  | dues and subscriptions | 3169 | 115078 | 3169 | 0 | 118247 |  |  |  |  | 0 | 118247 | indirect costs missing
NL | 45_PHILIPS |  | 2287557 |  | Salary costs researchers | 2287557 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 2287557 | 0 | 2287557 |  | 907994 |  |  | 907994 | 3195551
IT | 46_POLITO | 126789 |  |  | Activities of employees of the POLITO within the WPs | 126789 | 2006.26 |  |  |  | 2006.26 |  |  |  |  | 0 | 201.01 |  |  |  | 201.01 |  |  |  |  | 0 | 37930 |  |  | Activities of assistant researchers within the WPs | 37930 | 166926.27 | 0 | 0 | 166926.27 |  |  |  |  | 0 | 166926.27 | indirect costs missing
ES | 47_RGB | 290667 |  |  |  | 290667 |  |  |  |  | 0 |  |  |  |  | 0 | 15000 |  |  |  | 15000 |  |  |  |  | 0 |  |  |  |  | 0 | 305667 | 0 | 0 | 305667 | 58133 |  |  |  | 58133 | 363800
FR | 48_SAGEM |  | 60480 |  |  | 60480 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 60480 | 0 | 60480 |  | 41126.4 |  |  | 41126.4 | 101606.4
IT | 49_SUN | 102066 |  |  | 25,09 PM effort of 7 senior - tenured - Researchers | 102066 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 102066 | 0 | 0 | 102066 | 51033 |  |  | 50% flat rate on personnel costs | 51033 | 153099
DE | 51_SIEMENS |  | 254528 |  | due to internal accounting deadlines, data is only available until 16.4.2014. The remainder will be reported in the next period. | 254528 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 254528 | 0 | 254528 |  | 156787 |  |  | 156787 | 411315
DE | 52_SISW |  | 140730.86 |  | Deliverables, admins, meetings, etc. | 140730.86 |  | 3958 |  | Board, technical meetings, customer visit | 3958 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 144688.86 | 0 | 144688.86 |  |  |  |  | 0 | 144688.86 | indirect costs missing
FR | 54_SOYATEC | 208684 |  |  |  | 208684 | 17108 |  |  |  | 17108 | 1302 |  |  |  | 1302 |  |  |  |  | 0 |  |  |  |  | 0 | 143176 |  |  |  | 143176 | 370270 | 0 | 0 | 370270 | 25300 |  |  |  | 25300 | 395570
SE | 55_SYS | 120922 |  |  |  | 120922 | 1381 |  |  |  | 1381 |  |  |  |  | 0 |  |  |  |  | 0 | 14698 |  |  |  | 14698 |  |  |  |  | 0 | 137001 | 0 | 0 | 137001 | 74758 |  |  |  | 74758 | 211759
NL | 56_TU/e |  | 179089 |  |  | 179089 |  | 7000 |  |  | 7000 |  |  |  |  | 0 |  | 3000 |  |  | 3000 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 189089 | 0 | 189089 |  | 192318 |  |  | 192318 | 381407
DE | 57_TUB | 119414.56 |  |  |  | 119414.56 | 5077.34 |  |  |  | 5077.34 | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 124491.9 | 0 | 0 | 124491.9 | 24898.38 |  |  |  | 24898.38 | 149390.28
DE | 58_IST |  | 55463.71 |  |  | 55463.71 |  | 1317.5 |  |  | 1317.5 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 56781.21 | 0 | 56781.21 |  | 66556.45 |  |  | 66556.45 | 123337.66
FR | 59_TASF |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | no input yet
ES | 60_TASE |  | 178060.0611 |  | Personel costs for 30 PM | 178060.0611 |  | 0 |  | Included in Indirect Costs | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 10128.77 |  | Include Artemisia Fees for 2013 and 1014 and the Audit Report for year 2013 cost. | 10128.77 | 0 | 188188.8311 | 0 | 188188.8311 |  | 35612.01 |  | 20% of personel costs | 35612.01 | 223800.8411
AT | 61_TRAIL |  | 86533.08 |  |  | 86533.08 |  | 2387.48 |  |  | 2387.48 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 88920.56 | 0 | 88920.56 |  | 12513.32 |  |  | 12513.32 | 101433.88
FR | 62_TGS |  | 812664.06 |  |  | 812664.06 |  | 8133.97 |  |  | 8133.97 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 820798.03 | 0 | 820798.03 |  | 553180.9387 |  |  | 553180.9387 | 1373978.9687
FR | 63_TRT |  | 108699 |  | 1907 heures x 57 €/h | 812664.06 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 108699 | 0 | 108699 |  | 73915.32 |  | Personnel costs x 68% | 73915.32 | 182614.32
AT | 64_TTTech |  | 494735.4019 |  |  | 494735.4019 |  | 2457.39 |  |  | 2457.39 |  | 772.81 |  |  | 772.81 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 497965.6019 | 0 | 497965.6019 |  | 209525.8578 |  |  | 209525.8578 | 707491.4597
ES | 65_UC3M | 29977.9 |  |  |  | 29977.9 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 1002.94 |  |  |  | 1002.94 | 30980.84 | 0 | 0 | 30980.84 | 6196.17 |  |  |  | 6196.17 | 37177.01
DE | 66_ALU-FR | 87281.97 |  |  | 18 PM | 87281.97 | 233.52 |  |  |  | 233.52 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 87515.49 | 0 | 0 | 87515.49 | 14720.69 |  |  |  | 14720.69 | 102236.18
IT | 67_UNIGE-DITEN |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | no input yet
IT | 68_UNIFED-II | 272945.18 |  |  |  | 272945.18 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 272945.18 | 0 | 0 | 272945.18 | 136472.59 |  |  |  | 136472.59 | 409417.77
FR | 69_Valeo-F |  | 30975 |  | 525,40 h | 30975 |  | 1515.18 |  |  | 1515.18 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 32490.18 | 0 | 32490.18 |  | 21063 |  | Management | 21063 | 53553.18
SE | 71_VOLVO |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | no input yet, internal reporting process took longer
| SUM | 3974554.86 | 8708848.3434 | 1259471.6977 |  | 14600209.9611 | 70188.72 | 160929.2169 | 7282 |  | 238399.9369 | 9709.22 | 772.81 | 0 |  | 10482.03 | 17362.01 | 20529.94 | 0 |  | 37436.9 | 37648 | 70587.5 | 0 |  | 108235.5 | 213501.26 | 25230.8492 | 307564 |  | 546296.1092 | 4322964.07 | 8986898.6595 | 1574317.6977 | 14884180.4272 | 932287.0165 | 4855897.0725 | 361669.3488 | 0 | 6149853.4379 | 21034033.8651
AT | [5 empty] | 2180061.6598 |  |  |  |  | 57875.75 |  |  |  |  | 772.81 |  |  |  |  | 17464.27 |  |  |  |  | 0 |  |  |  |  | 4025.93 |  |  |  | 2256339.4698 |  |  |  |  | 1389801.9815 | 3646141.4514
BE | [5 empty] | 1025212 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 307564 |  |  |  | 1332776 |  |  |  |  | 205042 | 1537818
CZ | [5 empty] | 133110.0773 |  |  |  |  | 11177.4569 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 1790.0392 |  |  |  | 146077.5734 |  |  |  |  | 28958.9147 | 175036.4881
DE | [5 empty] | 2499763.56 |  |  |  |  | 77028.81 |  |  |  |  | 0 |  |  |  |  | 550 |  |  |  |  | 0 |  |  |  |  | 14867.44 |  |  |  | 2592209.81 |  |  |  |  | 922165.06 | 3514374.87
ES | [5 empty] | 1108775.6111 |  |  |  |  | 0 |  |  |  |  | 4522.5 |  |  |  |  | 16611 |  |  |  |  | 22950 |  |  |  |  | 33590.03 |  |  |  | 1186449.1411 |  |  |  |  | 221954.7165 | 1408403.8576
FR | [5 empty] | 2367385.12 |  |  |  |  | 36039.15 |  |  |  |  | 5186.72 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 143176 |  |  |  | 1894451.93 |  |  |  |  | 901551.9587 | 2796003.8887
IT | [5 empty] | 1093895.4429 |  |  |  |  | 2006.26 |  |  |  |  | 0 |  |  |  |  | 201.01 |  |  |  |  | 10000 |  |  |  |  | 37930 |  |  |  | 1144032.7129 |  |  |  |  | 432033.2214 | 1576065.9343
NL | [5 empty] | 3042149.95 |  |  |  |  | 20610.79 |  |  |  |  | 0 |  |  |  |  | 4090.62 |  |  |  |  | 60587.5 |  |  |  |  | 3352.67 |  |  |  | 3130791.53 |  |  |  |  | 1724613.995 | 4855405.525
SE | [5 empty] | 511301 |  |  |  |  | 15953 |  |  |  |  | 0 |  |  |  |  | 2836 |  |  |  |  | 14698 |  |  |  |  | 0 |  |  |  | 544788 |  |  |  |  | 234846 | 779634
UK | [5 empty] | 638555.54 |  |  |  |  | 17708.72 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 656264.26 |  |  |  |  | 88885.59 | 745149.85
[6 empty] | 14600209.9611 |  |  |  |  | 238399.9369 |  |  |  |  | 10482.03 |  |  |  |  | 37436.9 |  |  |  |  | 108235.5 |  |  |  |  | 546296.1092 |  |  |  | 14884180.4272 |  |  |  |  | 6149853.4379 | 21034033.8651

## PM_STATUS_TABLE_PARTNER
Partner |  | SUM Partner | WP1_01 | WP1_02 | WP1_03 | WP2_00 | WP2_01 | WP2_02 | WP2_03 | WP2_04 | WP2_05 | WP2_06 | WP2_07 | WP2_08 | WP2_09 | WP2_10 | WP2_11 | WP3_00 | WP3_01 | WP3_02 | WP3_03 | WP3_04 | WP3_05 | WP3_06 | WP3_07 | WP3_08 | WP4_00 | WP4_01 | WP4_02 | WP4_03 | WP4_04 | WP4_05 | WP4_06 | WP4_07 | WP5_00 | WP5_01 | WP5_02 | WP5_03 | WP5_04 | WP6_00 | WP6_01 | WP6_02 | WP6_03 | WP6_04 | WP6_05 | WP6_06 | WP6_07 | WP6_08 | WP6_09 | WP6_10 | WP6_11 | WP6_12 | WP6_13
01_AVL | Plan | 177.83 | 22 | 3.5 | 0.33 | [15 empty] | 29 | 53 |  |  | 0.5 | 0.5 | [14 empty] | 1.5 |  | 3 |  |  |  |  | 4 |  | 7.5 |  | 2.5 | 50.5
01_AVL | Actual | 176.91 | 22.31 | 3.45 | 0.3 | [15 empty] | 29.21 | 51.73 |  |  | 0.5 | 0.5 | [14 empty] | 1.38 |  | 3.5 |  |  |  |  | 3.9 |  | 7.17 |  | 2.5 | 50.46
02_A-F | Plan | 9.45 | 0.55 | 0.4 |  | 1 | [7 empty] | 0.8 | 0.76 | 4.7 | [24 empty] | 0.8 | 0.22 |  |  |  | 0.22
02_A-F | Actual | 8.71 | 0.5 | 0.35 |  | 0.8 | [7 empty] | 0.8 | 0.76 | 4.7 | [24 empty] | 0.8 | 0 |  |  |  | 0
03_A-G | Plan | 10 |  |  |  |  | 10
03_A-G | Actual | 9 |  |  |  |  | 9
04_A-UK | Plan | 8 | [14 empty] | 8
04_A-UK | Actual | 5 | [14 empty] | 5
05_ALA | Plan | 55.6 | 0.8 | 3.4 |  |  |  | 20.9 | [5 empty] | 13.3 | 2.3 | [25 empty] | 1.1 | 11.3 | [5 empty] | 2.5
05_ALA | Actual | 59.9 | 0.9 | 2.7 |  |  |  | 21 | [5 empty] | 14.6 | 3.5 | [25 empty] | 1.7 | 14.6 | [5 empty] | 0.9
06_ALS | Plan | 11 | [35 empty] | 11
06_ALS | Actual | 10.5 | [35 empty] | 10.5
07_ASTS | Plan | 10.6 |  |  | 0 | [29 empty] | 2 | 4.7 |  |  | 1.3 | [12 empty] | 2.6
07_ASTS | Actual | 10.25 |  |  | 0 | [29 empty] | 2 | 4.6 |  |  | 1.15 | [12 empty] | 2.5
08_ARCC | Plan | 10.1 |  |  | 0.2 | [13 empty] | 3 | [25 empty] | 6.9
08_ARCC | Actual | 8.2 |  |  | 0 | [13 empty] | 2 | [25 empty] | 6.2
09_ARCT | Plan | 13 | [40 empty] | 13
09_ARCT | Actual | 8 | [40 empty] | 8
10_AIT | Plan | 28.8 |  | 0.5 | [14 empty] | 2.5 |  | 1 | [14 empty] | 1.5 | 5 |  |  |  | 0.3 |  | 3 | 15
10_AIT | Actual | 35.9 |  | 1 | [14 empty] | 4.5 |  | 0.5 | [14 empty] | 1.1 | 3 |  |  |  | 0.3 |  | 3.5 | 22
11_AVL-S | Plan | 19.5 |  |  | 0.68 | [12 empty] | 7.38 |  |  | 10.89 |  |  |  | 0.55
11_AVL-S | Actual | 19.63 |  |  | 0.2 | [12 empty] | 7.6 |  |  | 11.51 |  |  |  | 0.32
12_AVL-R | Plan | 25.4 |  |  | 0.3 | [16 empty] | 9.4 |  |  | 0.7 | 0.6 | [18 empty] | 3.2 | [5 empty] | 0.9 | 9.4 | 0.9
12_AVL-R | Actual | 24.9 |  |  | 0.2 | [16 empty] | 9.4 |  |  | 0.6 | 0.6 | [18 empty] | 2.8 | [5 empty] | 1 | 9.4 | 0.9
13_BARCO | Plan | 127.25 |  |  | 0.25 | [21 empty] | 1 |  |  |  | 34 | 90 | [10 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.5 | 0.5
13_BARCO | Actual | 132.25 |  |  | 0.25 | [21 empty] | 1 |  |  |  | 36 | 93 | [10 empty] | 0.5 |  |  |  |  | 0.5 |  | 0.5 | 0.5
14_REUSE | Plan | 16 |  | 1 | [5 empty] | 1 | [36 empty] | 14
14_REUSE | Actual | 16.1 |  | 0.5 | [5 empty] | 1 | [36 empty] | 14.6
15_CRF | Plan | 15 | [20 empty] | 13.5 |  | 0.75 | 0.75
15_CRF | Actual | 15 | [20 empty] | 13.5 |  | 0.75 | 0.75
16_CTH | Plan | 13.3 |  | 0.3 | [14 empty] | 4 |  |  | 2 | [20 empty] | 4 | [8 empty] | 3
16_CTH | Actual | 10.34 |  | 0.03 | [14 empty] | 3.14 |  |  | 2.08 | [20 empty] | 3.47 | [8 empty] | 1.62
17_CIC | Plan | 6 | [38 empty] | 6
17_CIC | Actual | 6 | [38 empty] | 6
18_DAIMLER | Plan | 26 | [17 empty] | 24 |  |  |  |  | 1 | 1
18_DAIMLER | Actual | 24 | [17 empty] | 22 |  |  |  |  | 1 | 1
19_EADS-CAS | Plan | 30.2 | 1 | 1 | 0.2 | 1 |  |  | 23.4 |  |  |  |  | 0.9 | 0.7 | [28 empty] | 0.2 |  |  | 1.2 | 0.2 |  | 0.2 | 0.2
19_EADS-CAS | Actual | 25.1 | 0.9 | 0.7 | 0.1 | 0.9 |  |  | 20.6 |  |  |  |  | 0.5 | 0.2 | [28 empty] | 0.1 |  |  | 0.8 | 0.1 |  | 0.1 | 0.1
20_EADS IW-G | Plan | 30 |  | 1.67 | 0.33 | 0.67 | 1 |  | 2.33 |  |  |  |  | 4 | [29 empty] | 4.67 |  | 4.67 | 1.67 | 3.33 |  | 2.33 | 3.33
20_EADS IW-G | Actual | 30 |  | 3 | 0 | 0.6 | 1.5 |  | 0.7 |  |  |  |  | 12.5 | [29 empty] | 1.5 |  | 4 | 0.5 | 0 |  | 0.2 | 5.5
21_EADS IW-F | Plan | 6 | [12 empty] | 6
21_EADS IW-F | Actual | 3 | [12 empty] | 3
22_EADS IW-UK | Plan | 33.4 |  | 3 |  |  | 4 | [6 empty] | 1.7 | [25 empty] | 2 | 9 | 3 |  | 3.3 |  | 2 |  | 2.7 |  |  | 2.7
22_EADS IW-UK | Actual | 17.5 |  | 1 |  |  | 1.5 | [6 empty] | 1 | [25 empty] | 5 | 3 | 1 |  | 0 |  | 5 |  | 0 |  |  | 0
23_Elektrobit | Plan | 12 | [21 empty] | 12 | [20 empty] | 0
23_Elektrobit | Actual | 8 | [21 empty] | 8 | [20 empty] | 0
24_TUG | Plan | 7 |  | 1 | [17 empty] | 1 | [21 empty] | 4 | [8 empty] | 1
24_TUG | Actual | 6.24 |  | 0.89 | [17 empty] | 0.89 | [21 empty] | 3.57 | [8 empty] | 0.89
25_FBK | Plan | 16 | [38 empty] | 3.5 | 6.5 | 3 | 3
25_FBK | Actual | 16 | [38 empty] | 3.5 | 6.5 | 3 | 3
26_FhG | Plan | 39.99 |  |  | 0.33 |  | 3.33 |  | 3.33 | [11 empty] | 5 | 5 | [18 empty] | 3 | 2 | 5 | 4 |  | 2.67 |  |  |  | 3.33 |  |  | 3
26_FhG | Actual | 40.84 |  |  | 0.2 |  | 3.4 |  | 3.5 | [11 empty] | 5.1 | 5.1 | [18 empty] | 3 | 2.64 | 4.9 | 4.2 |  | 2 |  |  |  | 3.8 |  |  | 3
27_Tecnalia | Plan | 43.65 | [8 empty] | 12 | [32 empty] | 14.35 | [5 empty] | 17.3
27_Tecnalia | Actual | 43.65 | [8 empty] | 12 | [32 empty] | 14.35 | [5 empty] | 17.3
28_GMV | Plan | 9.7 | 0.7 | 0.5 | [6 empty] | 6.6 | [32 empty] | 0.6 |  |  |  |  | 1.3
28_GMV | Actual | 3.55 | 0.7 | 0.4 | [6 empty] | 1.65 | [32 empty] | 0.6 |  |  |  |  | 0.2
29_HON | Plan | 40 | [9 empty] | 40
29_HON | Actual | 40 | [9 empty] | 40
30_IBM UK | Plan | 17 | 0.1 | [37 empty] | 9.1 | [6 empty] | 0 |  | 0 | 7.8
30_IBM UK | Actual | 7.4 | 0.1 | [37 empty] | 4.2 | [6 empty] | 0 |  | 0 | 3.1
31_IFX-UK | Plan | 21.8 |  | 0.2 | [16 empty] | 5.2 | [22 empty] | 9.4 | 2.6 | [6 empty] | 4.4
31_IFX-UK | Actual | 22.1 |  | 0.2 | [16 empty] | 5.2 | [22 empty] | 9.7 | 2.6 | [6 empty] | 4.4
32_ITI | Plan | 65.5 |  | 0.5 | [6 empty] | 2.5 | [21 empty] | 9.5 | 4 | [6 empty] | 10.5 | 6.5 | 18 |  |  | 7 |  | 7
32_ITI | Actual | 67.33 |  | 0.2 | [6 empty] | 2.5 | [21 empty] | 9.98 | 2.45 | [6 empty] | 8.8 | 12.2 | 19.1 |  |  | 6.1 |  | 6
33_ITKE | Plan | 16.9 | [17 empty] | 11.9 | [22 empty] | 2.6 | 1.6 | 0.5 | [7 empty] | 0.3
33_ITKE | Actual | 13.8 | [17 empty] | 9.7 | [22 empty] | 2.1 | 1.3 | 0.4 | [7 empty] | 0.3
34_VIF | Plan | 38.34 |  | 1 | [13 empty] | 1 |  |  | 5.67 | 6 |  |  | 5.67 | [17 empty] | 6.3 | [6 empty] | 6.7 |  |  | 6
34_VIF | Actual | 30.4 |  | 1 | [13 empty] | 1 |  |  | 4 | 5 |  |  | 4.4 | [17 empty] | 5 | [6 empty] | 5 |  |  | 5
35_ALL4TEC | Plan | 20 | [33 empty] | 8 | [7 empty] | 12
35_ALL4TEC | Actual | 20 | [33 empty] | 8 | [7 empty] | 12
36_MU | Plan | 12 | [9 empty] | 6 | [31 empty] | 6
36_MU | Actual | 12 | [9 empty] | 6 | [31 empty] | 6
37_MATE | Plan | 43 | [33 empty] | 4 | [6 empty] | 1 | [8 empty] | 38
37_MATE | Actual | 46 | [33 empty] | 4 | [6 empty] | 1 | [8 empty] | 41
38_IBM NL | Plan | 12 | [16 empty] | 0 | [8 empty] | 0 | 2 | 2 | 2 | 2 | 0 | 0 | [8 empty] | 0 | [7 empty] | 4
38_IBM NL | Actual | 8.8 | [16 empty] | 0.2 | [8 empty] | 3.5 | 0.7 | 0.2 | 0.7 | 2.5 | 0.2 | 0.2 | [8 empty] | 0.1 | [7 empty] | 0.5
39_TNO | Plan | 85.4 |  |  | 0 | [22 empty] | 16 | 8 | 4 |  | 7 | 4 | 8.7 | [8 empty] | 20 | 2.7 |  | 6 |  |  |  | 4 | 5
39_TNO | Actual | 67.2 |  |  | 0 | [22 empty] | 15.6 | 11.4 | 4.4 |  | 4.3 | 3.4 | 7.7 | [8 empty] | 9.8 | 2.3 |  | 4.8 |  |  |  | 2 | 1.5
40_Obeo | Plan | 53.25 |  | 2 | [37 empty] | 0.25 | [6 empty] | 51
40_Obeo | Actual | 53.35 |  | 2.1 | [37 empty] | 0.25 | [6 empty] | 51
41_OFFIS | Plan | 45.9 | 0.7 | 0.6 | 1 |  |  |  |  | 1.2 | [8 empty] | 0.45 |  |  | 0.45 | [18 empty] | 12 | 7 |  |  | 4.5 |  | 18
41_OFFIS | Actual | 41.05 | 0.6 | 0.5 | 1 |  |  |  |  | 1.5 | [8 empty] | 1 |  |  | 0.5 | [18 empty] | 10 | 4.5 |  |  | 4 |  | 17.45
42_ORB | Plan | 36 | [8 empty] | 12 | [38 empty] | 12 | 12
42_ORB | Actual | 27 | [8 empty] | 12 | [38 empty] | 12 | 3
43_PTC | Plan | 4.9 | [17 empty] | 1.4 | 1.4 | 1.5 | [28 empty] | 0.6
43_PTC | Actual | 2.6 | [17 empty] | 0.9 | 0.6 | 0.8 | [28 empty] | 0.3
44_PS-Tech | Plan | 17 | [25 empty] | 7 | [14 empty] | 10
44_PS-Tech | Actual | 13.5 | [25 empty] | 5.5 | [14 empty] | 8
45_PHILIPS | Plan | 263.4 | 0.7 |  | 0.7 | [21 empty] | 9 | 75 | 70 | 70 |  |  |  | 4 | [8 empty] | 5 |  |  | 5 |  | 11 |  | 3 | 10
45_PHILIPS | Actual | 266.7 | 0.7 |  | 0.5 | [21 empty] | 9 | 88 | 70 | 68 |  |  |  | 0.5 | [8 empty] | 5 |  |  | 5 |  | 10 |  | 3 | 7
46_POLITO | Plan | 38 |  | 1.5 |  |  |  | 15 | [5 empty] | 16 | 5.5
46_POLITO | Actual | 30.7 |  | 0.9 |  |  |  | 9.5 | [5 empty] | 14.8 | 5.5
47_RGB | Plan | 67.32 |  |  | 0.33 | [21 empty] | 1 | [5 empty] | 59 | 1.33 | [8 empty] | 1.33 |  |  | 1.67 |  | 1.33 |  |  | 1.33
47_RGB | Actual | 67.32 |  |  | 0.33 | [21 empty] | 1 | [5 empty] | 59 | 1.33 | [8 empty] | 1.33 |  |  | 1.67 |  | 1.33 |  |  | 1.33
48_SAGEM | Plan | 10.1 | 0.6 |  |  | 0.2 |  |  |  | 6 |  |  |  |  | 0.4 | [25 empty] | 0.7 | 0.5 |  |  |  |  | 1.7
48_SAGEM | Actual | 9.2 | 0.7 |  |  | 0.4 |  |  |  | 5 |  |  |  |  | 0.2 | [25 empty] | 0.7 | 0.2 |  |  |  |  | 2
49_SUN | Plan | 27.17 | [33 empty] | 3.17 | [6 empty] | 2.67 | [8 empty] | 21.33
49_SUN | Actual | 25.08 | [33 empty] | 2.92 | [6 empty] | 2.46 | [8 empty] | 19.7
51_SIEMENS | Plan | 33 | [38 empty] | 3.7 |  |  | 11 | [5 empty] | 11 | 7.3
51_SIEMENS | Actual | 25.8 | [38 empty] | 3.5 |  |  | 8.2 | [5 empty] | 9.9 | 4.2
52_SISW | Plan | 36 | [45 empty] | 36
52_SISW | Actual | 12 | [45 empty] | 12
54_SOYATEC | Plan | 93.6 | [46 empty] | 93.6
54_SOYATEC | Actual | 23 | [46 empty] | 23
55_SYS | Plan | 21.3 |  |  | 0.3 | [13 empty] | 12 | [21 empty] | 2 | 1 | [5 empty] | 6
55_SYS | Actual | 49.27 |  |  | 0.07 | [13 empty] | 13 | [21 empty] | 1.1 | 0.1 | [5 empty] | 35
56_TU/e | Plan | 54 | [24 empty] | 6 |  | 7 | 22 |  | 6 |  | 2 | [11 empty] | 6 |  |  |  | 5
56_TU/e | Actual | 36 | [24 empty] | 6 |  | 5.5 | 13.5 |  | 5 |  | 2 | [11 empty] | 3 |  |  |  | 1
57_TUB | Plan | 22 | [17 empty] | 21 | [5 empty] | 1
57_TUB | Actual | 22 | [17 empty] | 21 | [5 empty] | 1
58_IST | Plan | 14.5 | [18 empty] | 3 | 3 | [18 empty] | 3 | 2.5 | [10 empty] | 3
58_IST | Actual | 14.5 | [18 empty] | 3 | 3 | [18 empty] | 3 | 2.5 | [10 empty] | 3
59_TASF | Plan | 2 | [10 empty] | 2
59_TASF | Actual | 1.56 | [10 empty] | 1.56
60_TASE | Plan | 30 | [8 empty] | 27 | [29 empty] | 1.5 | [8 empty] | 1.5
60_TASE | Actual | 30 | [8 empty] | 27 | [29 empty] | 1.5 | [8 empty] | 1.5
61_TRAIL | Plan | 19.5 | [32 empty] | 1.5 |  | 18 | [5 empty] | 0
61_TRAIL | Actual | 10.4 | [32 empty] | 1.4 |  | 9 | [5 empty] | 0
62_TGS | Plan | 99 | [46 empty] | 99
62_TGS | Actual | 86 | [46 empty] | 86
63_TRT | Plan | 36 | [46 empty] | 36
63_TRT | Actual | 14 | [46 empty] | 14
64_TTTech | Plan | 87.31 | [15 empty] | 3.2 |  |  |  | 25.68 | [22 empty] | 58.43
64_TTTech | Actual | 86.74 | [15 empty] | 2.63 |  |  |  | 25.68 | [22 empty] | 58.43
65_UC3M | Plan | 23 |  | 0 | [5 empty] | 1 | [36 empty] | 22
65_UC3M | Actual | 17 |  | 1 | [5 empty] | 1 | [36 empty] | 15
66_ALU-FR | Plan | 12 | [17 empty] | 12
66_ALU-FR | Actual | 18 | [17 empty] | 18
67_UNIGE-DITEN | Plan | 7 | [20 empty] | 7
67_UNIGE-DITEN | Actual | 9 | [20 empty] | 9
68_UNIFED-II | Plan | 51.96 | [33 empty] | 7.26 |  |  |  |  | 3.1 | 5 | 2.2 |  |  |  |  | 1 |  |  |  | 33.4
68_UNIFED-II | Actual | 49.66 | [33 empty] | 7.26 |  |  |  |  | 2.1 | 4.3 | 2.2 |  |  |  |  | 0.4 |  |  |  | 33.4
69_Valeo-F | Plan | 11.2 | [21 empty] | 11 | 0.1 | 0.1
69_Valeo-F | Actual | 10.2 | [21 empty] | 10 | 0.1 | 0.1
71_VOLVO | Plan | 38 | 0.7 | 0.3 | [13 empty] | 1 | 29 | [5 empty] | 1 | 1 | [14 empty] | 2 |  |  |  | 3
71_VOLVO | Actual | 30.4 | 0.4 | 0.1 | [13 empty] | 0.1 | 28.6 | [5 empty] | 0.5 | 0.1 | [14 empty] | 0.2 |  |  |  | 0.4
SUM WP | PLAN | 2437.12 | 27.85 | 22.37 | 4.95 | 2.87 | 18.33 | 35.9 | 29.06 | 9.2 | 60.1 | 46 | 2 | 36.7 | 15.66 | 4.7 | 8 | 12.58 | 50.95 | 70.3 | 61.16 | 107.03 | 20.5 | 23 | 10.27 | 4.95 | 17 | 98 | 87 | 98 | 36 | 105 | 72.5 | 20.03 | 3.5 | 28.63 | 23 | 11 | 1.3 | 2 | 72.8 | 45.77 | 100.6 | 91.82 | 79.13 | 35.23 | 58.57 | 75.56 | 280.9 | 74.36 | 55.66 | 114.63 | 64.7
SUM WP | ACTUAL | 2191.53 | 27.81 | 20.02 | 3.15 | 2.7 | 15.4 | 30.5 | 24.8 | 8.5 | 55.15 | 46 | 1.56 | 44.2 | 13.16 | 4.7 | 5 | 11.33 | 52.44 | 71.6 | 59.12 | 104.18 | 22.5 | 18 | 8.17 | 4.05 | 17 | 112.6 | 87.6 | 86.1 | 36.7 | 104.8 | 72.58 | 14.18 | 3.4 | 27.88 | 12 | 10.5 | 1.15 | 5 | 54.78 | 48.79 | 82.96 | 88.82 | 74.83 | 31.57 | 50.35 | 70.13 | 174.2 | 63.47 | 28.03 | 114.52 | 63.55
Note on BD1: Hamedler Annemarie: This table has been reported in the annual report in M12 to JU.

## Sheet2
Country | Partner | Personal costs (direct) | Travel costs (direct) | durable equipment costs (direct) | Costs for consumables (direct) | costs for subcontracting (direct) | Other costs (direct) | Sum direct costs | Indirect Costs | Overall costs to the JU (direct & indirect costs)
AT | 01_AVL | 1148964.0415 | 40135.61 | 0 | 0 | 0 | 3860.95 | 1192960.6015 | 936405.6938 | 2129366.2954
FR | 02_A-F | 130000 | 2000 | 0 | 0 | 0 | 0 | 132000 | 0 | 132000
DE | 03_A-G | 121000 | 3000 | 0 | 0 | 0 | 0 | 124000 | 5000 | 129000
UK | 04_A-UK | 180000 | 2000 | 0 | 0 | 0 | 0 | 182000 | 0 | 182000
IT | 05_ALA | 255000 | 0 | 0 | 0 | 0 | 0 | 255000 | 127500 | 382500
FR | 06_ALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT | 07_ASTS | 50437.6829 | 0 | 0 | 0 | 0 | 0 | 50437.6829 | 25218.8414 | 75656.5243
SE | 08_ARCC | 70036 | 0 | 0 | 0 | 0 | 0 | 70036 | 14007 | 84043
SE | 09_ARCT | 91200 | 1900 | 0 | 0 | 0 | 0 | 93100 | 4164 | 97264
AT | 10_AIT | 247165.5864 | 5923.47 | 0 | 13603.32 | 0 | 0 | 266692.3764 | 172991.1939 | 439683.5703
DE | 11_AVL-S | 143806.7 | 7223.63 | 0 | 0 | 0 | 0 | 151030.33 | 86053.44 | 237083.77
DE | 12_AVL-R | 166117 | 5064 | 0 | 0 | 0 | 0 | 171181 | 0 | 171181
BE | 13_BARCO | 1025212 | 0 | 0 | 0 | 0 | 307564 | 1332776 | 205042 | 1537818
ES | 14_REUSE | 77191.54 | 0 | 3799 | 0 | 0 | 2667 | 83657.54 | 15438.31 | 99095.85
IT | 15_CRF | 61609.84 | 0 | 0 | 0 | 10000 | 0 | 71609.84 | 30804.92 | 102414.76
SE | 16_CTH | 63595 | 10406 | 0 | 2836 | 0 | 0 | 76837 | 29186 | 106023
UK | 17_CIC | 46968 | 2444 | 0 | 0 | 0 | 0 | 49412 | 2540 | 51952
DE | 18_DAIMLER | 280000 | 3000 | 0 | 0 | 0 | 0 | 283000 | 11000 | 294000
DE | 19_EADS-CAS | 286562.71 | 4491.87 | 0 | 0 | 0 | 0 | 291054.58 | 45936 | 336990.58
DE | 20_EADS IW-G | 295354.45 | 10688.35 | 0 | 0 | 0 | 5933.44 | 311976.24 | 152222.75 | 464198.99
FR | 21_EADS IW-F | 24543 | 0 | 0 | 0 | 0 | 0 | 24543 | 31170 | 55713
UK | 22_EADS IW-UK | 58034 | 5246 | 0 | 0 | 0 | 0 | 63280 | 52812 | 116092
FR | 23_Elektrobit | 58034 | 0 | 0 | 0 | 0 | 0 | 108548.72 | 1628.3 | 110177.02
AT | 24_TUG | 27144.58 | 17.2 | 0 | 0 | 0 | 0 | 27161.78 | 5428.916 | 32590.696
IT | 25_FBK | 77847.74 | 0 | 0 | 0 | 0 | 0 | 0 | 38923.87 | 38923.87
DE | 26_FhG | 250237 | 9435 | 0 | 550 | 0 | 8934 | 269156 | 174833 | 443989
ES | 27_Tecnalia | 208719.88 | 0 | 0 | 295 | 0 | 7364.33 | 216379.21 | 41743.98 | 258123.19
ES | 28_GMV | 19967.25 | 0 | 0 | 0 | 0 | 275 | 20242.25 | 3993.45 | 24235.7
CZ | 29_HON | 108255.0773 | 4469.4569 | 0 | 0 | 0 | 1790.0392 | 114514.5734 | 22902.9147 | 137417.4881
UK | 30_IBM UK | 70153.54 | 8018.72 | 0 | 0 | 0 | 0 | 0 | 33533.59 | 33533.59
UK | 31_IFX-UK | 283400 | 0 | 0 | 0 | 0 | 0 | 283400 | 0 | 283400
ES | 32_ITI | 242988.98 | 0 | 0 | 0 | 22950 | 12151.99 | 278090.97 | 48597.7965 | 326688.7665
DE | 33_ITKE | 72578.12 | 835.04 | 0 | 0 | 0 | 0 | 73413.16 | 148988.42 | 222401.58
AT | 34_VIF | 175518.97 | 6954.6 | 0 | 0 | 0 | 164.98 | 182638.55 | 52937 | 235575.55
SE | 35_ALL4TEC | 165548 | 2266 | 0 | 0 | 0 | 0 | 167814 | 112731 | 280545
CZ | 36_MU | 24855 | 6708 | 0 | 0 | 0 | 0 | 31563 | 6056 | 37619
IT | 37_MATE | 147200 | 0 | 0 | 0 | 0 | 0 | 147200 | 22080 | 169280
NL | 38_IBM NL | 97301.03 | 4812.01 | 0 | 0 | 0 | 0 | 102113.04 | 48650.515 | 150763.555
NL | 39_TNO | 363124.92 | 8798.78 | 0 | 1090.62 | 60587.5 | 183.67 | 433785.49 | 575651.48 | 1009436.97
FR | 40_Obeo | 229341 | 7282 | 0 | 0 | 0 | 0 | 236623 | 154168 | 390791
DE | 41_OFFIS | 201188.48 | 17404.56 | 0 | 0 | 0 | 0 | 218593.04 | 30068.93 | 248661.97
ES | 42_ORB | 61203 | 0 | 723.5 | 1316 | 0 |  | 63242.5 | 12240 | 75482.5
DE | 43_PTC | 25500 | 5300 | 0 | 0 | 0 | 0 | 30800 | 5100 | 35900
NL | 44_PS-Tech | 115078 | 0 | 0 | 0 | 0 | 3169 | 118247 | 0 | 118247
NL | 45_PHILIPS | 2287557 | 0 | 0 | 0 | 0 | 0 | 2287557 | 907994 | 3195551
IT | 46_POLITO | 126789 | 2006.26 | 0 | 201.01 | 0 | 37930 | 166926.27 | 0 | 166926.27
ES | 47_RGB | 290667 | 0 | 0 | 15000 | 0 | 0 | 305667 | 58133 | 363800
FR | 48_SAGEM | 60480 | 0 | 0 | 0 | 0 | 0 | 60480 | 41126.4 | 101606.4
IT | 49_SUN | 102066 | 0 | 0 | 0 | 0 | 0 | 102066 | 51033 | 153099
DE | 51_SIEMENS | 254528 | 0 | 0 | 0 | 0 | 0 | 254528 | 156787 | 411315
DE | 52_SISW | 140730.86 | 3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FR | 54_SOYATEC | 208684 | 17108 | 1302 | 0 | 0 | 143176 | 370270 | 0 | 370270
SE | 55_SYS | 120922 | 1381 | 0 | 0 | 14698 | 0 | 137001 | 74758 | 211759
NL | 56_TU/e | 179089 | 7000 | 0 | 3000 | 0 | 0 | 189089 | 192318 | 381407
DE | 57_TUB | 119414.56 | 5077.34 | 0 | 0 | 0 | 0 | 124491.9 | 24898.38 | 149390.28
DE | 58_IST | 55463.71 | 1317.5 | 0 | 0 | 0 | 0 | 56781.21 | 66556.45 | 123337.66
FR | 59_TASF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ES | 60_TASE | 178060.0611 | 0 | 0 | 0 | 0 | 10128.77 | 188188.8311 | 35612.01 | 223800.8411
AT | 61_TRAIL | 86533.08 | 2387.48 | 0 | 0 | 0 | 0 | 88920.56 | 12513.32 | 101433.88
FR | 62_TGS | 812664.06 | 8133.97 | 0 | 0 | 0 | 0 | 820798.03 | 553180.9387 | 1373978.9687
FR | 63_TRT | 812664.06 | 0 | 0 | 0 | 0 | 0 | 108699 | 73915.32 | 182614.32
AT | 64_TTTech | 494735.4019 | 2457.39 | 772.81 | 0 | 0 | 0 | 497965.6019 | 209525.8578 | 707491.4597
ES | 65_UC3M | 29977.9 | 0 | 0 | 0 | 0 | 1002.94 | 30980.84 | 6196.17 | 37177.01
DE | 66_ALU-FR | 87281.97 | 233.52 | 0 | 0 | 0 | 0 | 87515.49 | 14720.69 | 102236.18
IT | 67_UNIGE-DITEN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT | 68_UNIFED-II | 272945.18 | 0 | 0 | 0 | 0 | 0 | 272945.18 | 136472.59 | 409417.77
FR | 69_Valeo-F | 30975 | 1515.18 | 0 | 0 | 0 | 0 | 32490.18 | 21063 | 53553.18
SE | 71_VOLVO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUM | 14600209.9611 | 238399.9369 | 6597.31 | 37436.9 | 108235.5 | 546296.1092 | 14583471.5672 | 6124553.4379 | 20708025.0051
AT |  | 2180061.6598 | 57875.75 | 772.81 | 17464.27 | 0 | 4025.93 | 2256339.4698 | 1389801.9815 | 3646141.4514
BE |  | 1025212 | 0 | 0 | 0 | 0 | 307564 | 1332776 | 205042 | 1537818
CZ |  | 133110.0773 | 11177.4569 | 0 | 0 | 0 | 1790.0392 | 146077.5734 | 28958.9147 | 175036.4881
DE |  | 2499763.56 | 77028.81 | 0 | 550 | 0 | 14867.44 | 2447520.95 | 922165.06 | 3369686.01
ES |  | 1108775.6111 | 0 | 4522.5 | 16611 | 22950 | 33590.03 | 1186449.1411 | 221954.7165 | 1408403.8576
FR |  | 2367385.12 | 36039.15 | 1302 | 0 | 0 | 143176 | 1894451.93 | 876251.9587 | 2770703.8887
IT |  | 1093895.4429 | 2006.26 | 0 | 201.01 | 10000 | 37930 | 1066184.9729 | 432033.2214 | 1498218.1943
NL |  | 3042149.95 | 20610.79 | 0 | 4090.62 | 60587.5 | 3352.67 | 3130791.53 | 1724613.995 | 4855405.525
SE |  | 511301 | 15953 | 0 | 2836 | 14698 | 0 | 544788 | 234846 | 779634
UK |  | 638555.54 | 17708.72 | 0 | 0 | 0 | 0 | 578092 | 88885.59 | 666977.59
| SUM | 14600209.9611 | 238399.9369 | 6597.31 | 37436.9 | 108235.5 | 546296.1092 | 14583471.5672 | 6124553.4379 | 20708025.0051